## Test Case
Product Name | https://belasea.com/ |  |  |  | TC Start Date | 22/07/2023 |  | TC Execution Start Date | 25/07/2023 | TEST CASE SUMMARY
Module Name | Projects,Tasks |  |  |  | TC End Date | 24/07/2023 |  | TC Execution End Date | 28/07/2023 | Pass | 14
[5 empty] | Test Case Developed By | Israt Yeasin Era |  | Browser (tested) | No | FAIL | 4
Developer Name (TL) |  |  |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir |  | Performance (tested) | No | WARNING | 0
Test Executed by | [9 empty] | TOTAL | 18
Test Case ID/Name | Module | type of testing | Features | Test Case Description | Expected Result | Actual Result | Test Data | Reproducing Steps | Status | Remarks
TC00 | User Management | Functional Testing | sign up | Enter one alphabetic characters in the first and last name field | Should show an error message | Worked as not expected | a, b | 1.Go to https://belasea.com/account/register/ 2.Enter character a 3.click to sign up | FAIL
TC002 |  |  |  | Verify with invalid email address | Should show an error message | Worked as expected | abcd10 | 1.Go to https://belasea.com/account/register/ 2.Enter email 3.click to sign up | Pass | invalid email
TC003 |  |  |  | Verify with 11digit invalid number | Should show an error message | Worked as expected | 55555555555 | 1.Go to https://belasea.com/account/register/ 2.Enter number 3.click to sign up | Pass
TC004 |  |  |  | Verify with alphanumeric password | Should show an error message | Worked as expected | aaaaa10 | 1.Go to https://belasea.com/account/register/ 2.Enter password 3.click to sign up | Pass
TC005 |  |  |  | Verify with only numeric password | Should show an error message | Worked as expected | 9999999 | 1.Go to https://belasea.com/account/register/ 2.Enter number 999999999 3.click to sign up | Pass
TC006 |  |  |  | Enter password without special character | Should be accept the password | Worked as not expected | aaaaaaa | 1.Go to https://belasea.com/account/register/ 2.Enter password 3.click to sign up | FAIL
TC007 |  |  |  | Leave the password field empty | Should show an error message | Worked as expected | null | 1.Go to https://belasea.com/account/register/ 2.Not input password 3.click to sign up | Pass
TC008 |  |  |  | Enter wrong confirm password | Should show an error message | Worked as expected | 12344 |  | Pass
TC009 |  |  |  | Enter one alphabetic characters in the name field | Should not considered | Worked as expected | a | 1.Go to https://www.diamondworldltd.com/register 2.Enter name 3.click to sign up | Pass
TC010 |  |  |  | Enter infinity special chaaracter in name field | Should not considered | Worked as not expected | @@@@@@ | 1.Go to https://www.diamondworldltd.com/register 2.Enter name 3.click to sign up | FAIL
TC011 |  |  |  | Leave the Date of Birth field empty | Should show an error message | Worked as expected | null | 1.Go to https://www.diamondworldltd.com/register 2.Check Verification time | Pass
TC012 |  |  |  | Verify the Contact us field | Should move to the next field | Worked as expected |  | 1.Go to https://www.diamondworldltd.com/register 2.Enter "Contact us " field | Pass
TC013 |  |  |  | Verify with existing email and mobile number | Should show an error message | Worked as expected | 01735353536 | 1.Go to https://www.diamondworldltd.com/register 2.Enter existing email and mobile number 3.click to sign up | Pass
TC014 |  |  | Sign In | Verify the "Forgot password" feature with invalid email address | Should show an error message | Worked as expected | asd@dd | 1.Go to https://www.diamondworldltd.com/register 2.Enter "Forgot password" field 3.Enter invalid email | Pass
TC015 |  |  |  | Leave the email & password field empty | Should show an error message | Worked as expected |  |  | Pass
TC016 |  |  |  | Verify an error message should show if left the all field empty | Should not considered | Worked as expected |  |  | Pass
TC017 |  |  |  | Login button should be highlighted when curson move over here | Should highlighted | Worked as expected |  |  | Pass
TC018 |  |  |  | Enter invalid email in "Forgot password" field | Should not considered | Worked as not expected | mnb@2333ccc.com | 1.Go to https://www.diamondworldltd.com/register 2.Click forgot password 3.Enter invalid email | FAIL

## Test Report
Project Name: https://www.diamondworldltd.com/ Sprint - 19 No. of Features: 2 No. of test Cases: 25 Total Bugs: 8
Test Case Run |  |  |  |  | Compo￼nent wise
Status | Count
Passed | 14 |  |  |  | Total Bugs | Backend | Android | Backoffice
Blocked | 0 |  |  |  | 4 | 3 | 1 | 0
Untested | 0
Retest | 0
Failed | 4
| Severity | [5 empty] | Bug-Type
Component | Critical | Major | Minor | Low | Subtotal | Component | Functional | Visual | Content | Performance | Crash | Subtotal
Backend | 0 | 5 | 1 | 0 | 6 | Backend | 4 | 2 | 0 | 0 | 0 | 6
Android | 0 | 0 | 0 | 0 | 0 | Android | 0 | 0 | 0 | 0 | 0 | 0
Backoffice | 0 | 0 | 0 | 0 | 0 | Backoffice | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 5 | 1 | 0 |  | Total | 4 | 2 | 0 | 0 | 0 | 6
|  | Component vs Severity | [5 empty] | Component vs Bug-Type
Note on B3: Specify you test run ID from TestRail here

## Bug Report
TC001 ISSUE : Login with 11digit invalid number Reproducing Steps : 1.Go to https://belasea.com/account/register/ 2.Enter number 55555555555 3.click to sign up Enviroment : Production Module : Sign Up Severity : P1 Screenshot : Invalid Number Responsible QA : Era